## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Team-project-2235-swen-261-06-e-shakeandpour
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a admin of my e-store I want to login into my e-store with admin rights so that I have permissions to add, delete, and modify products in my inventory. | Given I am an admin when I login in with the username "admin" and password "1234" then I should see the admin dashboard with buttons to manage inventory. | Pass | AD 03/18/2024
| Given I am an admin when I try to login in with an incorrect password then I should see an error and prevent me from logging into the admin page | Pass | AD 03/18/2024
| Given I am an admin when I try to login with an inncorrect username then I should see an error and I should not be able to log into the admin page of the store | Pass | AD 03/18/2024
As an Owner I want to be able to create, update, and delete items in my inventory to keep the inventory up-to-date | Given I am logged in as a admin when I view the inventory management dashboard then I should be able to enter a product or kit's ID and delete it from the inventory | Pass | DF 03/18/2024
| Given I am logged in as a admin when I view the inventory management dashboard then I should be able to enter a product or kit's name, price, and quantity and add it to the inventory | Pass | DF 03/18/2024
| Given I am logged in as a admin when I view the inventory management dashboard then I should be able to enter a product or kit's id, name, price, and quantity and update its information in the inventory | Pass | DF 03/18/2024
| Given I am am admin when I logged in then I should not have access to the shopping cart. | Pass | DF 03/18/2024
As a Buyer I want to login to my account so I can view products so I can make a choice if I want to buy the product or not. | Given I am user when I login in with the username "testUser" and password "0000" then I should be logged into the user view of the website where I can access shopping carts as well as view kits | Pass | MM; 3/17/2024. AD; 3/18/2024
| Given I am an user when I try to login in with an incorrect password then I should see an error and prevent me from logging into the user page | Pass | MM; 3/17/2024. AD; 3/18/2024
| Given I am an user when I try to login in with an incorrect user then I should see an error and prevent me from logging into the user page | Pass | MM; 3/17/2024. AD; 3/18/2024
As a buyer I want to be able to browse drink kits and drinks so that I can purchase drink kits which interest me. | Given I am a buyer when I Click on view drink kits then I should see information about the drink kits that shows products in kit and the price. | Pass | MM; 3/18/2024
| Given I am buyer when I click off the view drink kits page then should not see the kits or information about them. | Pass | MM; 3/18/2024
As a buyer I want to be able to search for a drink kit by name so I can find what I’m looking for quickly. | Given I am buyer when I type certain words that matches a kit name then kits with those substrings in the name should pop up | Pass | AD 03/18/2024
| Given I am buyer when I type a string and there are no kits with that substring in their name then nothing should pop up for found kits | Pass | AD 03/18/2024
| Given I am a buyer when I type a string then kits with that substring in their name should popup then I should be able to add them to my cart view a add to cart button | Pass | AD 03/18/2024
As a buyer I want to be able to remove drink kits from my shopping cart so I can get rid of items I don't want anymore. | Given I am a user when I click the minus button for a kit inside the shopping cart then the item quantity will be decreased by 1. | Pass | MM; 3/17/2024
| Given I am user when I click the minus button from a kit in shopping cart and the item quantity reaches zero then the kit shold be completly removed from the cart | Pass | MM; 3/17/2024
| Given I am user when I remove an item from the shopping cart then all the prices should be changed to reflect quantity in the shopping cart | Pass | MM; 3/17/2024
| Given I am a user when I click the 'X' button for a kit inside the cart then the kit should be completely removed from the cart | Pass | MM; 3/18/2024
As a buyer I want to add drink kits to my shopping cart so I can see what I'm planning to buy | Given I am a user when I add a kit to my shopping cart then the kit should appear inside the cart. | Pass | MM; 3/18/2024
| Given I am a user when I add a kit that is already in the shopping cart then the kit's quantity should increase by 1. | Pass | MM; 3/18/2024
| Given I am user when I add a kit to my shopping then all the prices should update to reflect the quantity added | Pass | AD 03/18/2024
| Given I am a user when I click the plus button for a kit inside the shopping cart then the quantity of that kit should increase by 1 | Pass | AD 03/18/2024
SPRINT 3 CARDS
As a buyer I want to be able to select drink kits from a previous order to my shopping cart so I can repurchase drink kits I like | Given I am logged in as a user and have an order history when I select some, but not all, of the items in a past order then I can copy my selected items to my current shopping cart |  |  | Pass | MM 4/4/2024
| Given I am logged in as a user and have an order history when I select all of the items in a past order then I can copy my selected items to my current shopping cart |  |  | Pass | AD 4/4/2024
As a user I want to be able to purchase the drink kits in my shopping cart so I can use them. | Given I have a cart when I want to purchase the items in my cart then the shopping cart should become empty and order should be recorded into my history. |  |  | Pass | DD 4/4/2024
| Given I have an empty cart when I try to purchase the cart then an error message shows up that no items are in the cart |  |  | Pass | DD 4/4/2024
As a Buyer I want to register my information so I can keep track of my orders and information, such as payment and shipping address. | Given I am a new user when I create an account with a valid username and password then the server with say that registration is successful and I can login with said username and password |  |  | Pass | AD 4/2/2024
| Given I am a new user when I create an account with a username already in use then an error message pops up and the account is not created. |  |  | Pass | DF 4/2/2024
As a Buyer I want to filter my orders by specific kit names in the order so the I can repurchase orders which I enjoyed | Given I am a user when I search for a specific previously ordered kit then I expect to find drink kits that meet the specific requirements. |  |  | Pass | JB 4/4/2024
| Given I am a user when I type a string and there are no kits with that substring in their orders then nothing should pop up for found kits in order history. |  |  | Pass | JB 4/4/2024
As a Buyer I want to view a list of my previous orders so I can see information on them. | Given I am a user when I view my order history then I shoudl see all my previous orders. |  |  | Pass | MM 4/4/2024
| Given I am a user when I view my order history and I have no previous order then I should not see any information on the . |  |  | Pass | MM 4/4/2024
As a Buyer I want to update my person information so that my info is relevant when purchasing drink kits | Given I am a user when I cahnge my username and/or password then I can only log in with that information now. |  |  | Pass | DF 4/1/2024
| Given I am a user when I change my name then the site will update with my new name. |  |  | Pass | DF 4/1/2024
As a developer I want to implement the order history controller and DAO so that I can keep track of user order history. | Given I am a developer when I request the ordre history of a certain user with a certain id then I should get their order history returned to me |  |  | Pass | AD 3/31/2024
| Given I am a developer when I post using the correct oder format for a certain user then that order should be saved to that user's order history |  |  | Pass | DD 3/31/2024
As an buyer, I want to be able to create custom kits with certain products, so that I can create a customized kit that caters to my tastes. | Given I am a user when I make a customized kit then I should be able to purchase the kit. |  |  | Pass | MM 4/4/2024
| Given I am a user when add a product to my customized kit then the kit should be comprised of that product and any others I add |  |  | Pass | JB 4/4/2024