## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a admin of my e-store I want to login into my e-store with admin rights so that I have permissions to add, delete, and modify products in my inventory. | Given I am an admin when I login in with the username "admin" and password "1234" then I should see the admin dashboard with buttons to manage inventory. | Pass | AD 03/18/2024
| Given I am an admin when I try to login in with an incorrect password then I should see an error and prevent me from logging into the admin page | Pass | AD 03/18/2024
| Given I am an admin when I try to login with an inncorrect username then I should see an error and I should not be able to log into the admin page of the store | Pass | AD 03/18/2024
As an Owner I want to be able to create, update, and delete items in my inventory to keep the inventory up-to-date | Given I am logged in as a admin when I view the inventory management dashboard then I should be able to enter a product or kit's ID and delete it from the inventory | Pass | DF 03/18/2024
| Given I am logged in as a admin when I view the inventory management dashboard then I should be able to enter a product or kit's name, price, and quantity and add it to the inventory | Pass | DF 03/18/2024
| Given I am logged in as a admin when I view the inventory management dashboard then I should be able to enter a product or kit's id, name, price, and quantity and update its information in the inventory | Pass | DF 03/18/2024
| Given I am am admin when I logged in then I should not have access to the shopping cart. | Pass | DF 03/18/2024
As a Buyer I want to login to my account so I can view products so I can make a choice if I want to buy the product or not. | Given I am user when I login in with the username "testUser" and password "0000" then I should be logged into the user view of the website where I can access shopping carts as well as view kits | Pass | MM; 3/17/2024. AD; 3/18/2024
| Given I am an user when I try to login in with an incorrect password then I should see an error and prevent me from logging into the user page | Pass | MM; 3/17/2024. AD; 3/18/2024
| Given I am an user when I try to login in with an incorrect user then I should see an error and prevent me from logging into the user page | Pass | MM; 3/17/2024. AD; 3/18/2024
As a buyer I want to be able to browse drink kits and drinks so that I can purchase drink kits which interest me. | Given I am a buyer when I Click on view drink kits then I should see information about the drink kits that shows products in kit, the price, and quantity. | Pass | MM; 3/18/2024
| Given I am buyer when I click off the view drink kits page then should not see the kits or information about them. | Pass | MM; 3/18/2024
As a buyer I want to be able to search for a drink kit by name so I can find what I’m looking for quickly. | Given I am buyer when I type certain words that matches a kit name then kits with those substrings in the name should pop up | Pass | AD 03/18/2024
| Given I am buyer when I type a string and there are no kits with that substring in their name then nothing should pop up for found kits | Pass | AD 03/18/2024
| Given I am a buyer when I type a string then kits with that substring in their name should popup then I should be able to add them to my cart view a add to cart button | Pass | AD 03/18/2024
As a buyer I want to be able to remove drink kits from my shopping cart so I can get rid of items I don't want anymore. | Given I am a user when I click the minus button for a kit inside the shopping cart then the item quantity will be decreased by 1. | Pass | MM; 3/17/2024
| Given I am user when I click the minus button from a kit in shopping cart and the item quantity reaches zero then the kit shold be completly removed from the cart | Pass | MM; 3/17/2024
| Given I am user when I remove an item from the shopping cart then all the prices should be changed to reflect quantity in the shopping cart | Pass | MM; 3/17/2024
| Given I am a user when I click the 'X' button for a kit inside the cart then the kit should be completely removed from the cart | Pass | MM; 3/18/2024
As a buyer I want to add drink kits to my shopping cart so I can see what I'm planning to buy | Given I am a user when I add a kit to my shopping cart then the kit should appear inside the cart. | Pass | MM; 3/18/2024
| Given I am a user when I add a kit that is already in the shopping cart then the kit's quantity should increase by 1. | Pass | MM; 3/18/2024
| Given I am user when I add a kit to my shopping then all the prices should update to reflect the quantity added | Pass | AD 03/18/2024
| Given I am a user when I click the plus button for a kit inside the shopping cart then the quantity of that kit should increase by 1 | Pass | AD 03/18/2024